Neighbourhood Planning

Preparing a Neighbourhood Priorities Statement

# Proposed programme of engagement

Monthly sessions on a range of topics along with drop-in sessions to share progress, best practice, discuss issues etc. The sessions will also be used to complete highlight reports and to advise parishes of upcoming stages and keep an eye on how groups are progressing.

| Title | Content | When | Attendees |
| --- | --- | --- | --- |
| Publicity | Article in neighbourhood planning newsletter. Email to interested parishes to invite participation to take part. Web page – giving details of pilot parishes and to invite other parishes to register an interest in the next stage. | Late April |  |
| Introductory Event | General introduction to NPS, documentation, designation process, data and process, timescales, support offer. Expectations in terms of participation and timescales. Q and A. Parishes will be asked to confirm their participation within 10 days of the email following the event and submit designation request. CC support offer. | Month 1 15.00-15.45 Tuesday 28 April 2026 | All interested parishes |
| Understanding Data, Early Engagement, Analysing Responses | Designed to encourage early community engagement – options that you could use, plus how to encourage residents to complete the Lets Talk survey and a bit on how to analyse responses and review feedback. Will pick up on including this in a cons statement (although that will also be covered in the submitting session). | Month 2 10.30-11.30 Wednesday 3 June 2026 | All confirmed participants. |
| Topic: Understanding Your Places, Context, including Local Economy, Design, Character and Heritage | Session on how to identify strengths, weaknesses in your places. Introduction to the tables / templates to help you to think about what works well and what doesn’t, understanding your local economy; what do local businesses need to thrive. Consideration of heritage and design – which issues matter most to your communities. | Month 3 10.30-11.30 Wednesday 1 July 2026 | All confirmed participants. |
| Topic: Housing | Including understanding housing need – what kind of homes, local priorities, where should new homes go, call for sites. Explaining affordable housing, explaining housing numbers (standard method). The spatial approach in the Local Plan. | Month 4 10.30-11.30 Wednesday 12 August 2026 | All confirmed participants. |
| Topic: Infrastructure and Moving Around | Infrastructure – utilities, services, facilities. Active travel infrastructure, walkability. Public transport and parking. | Month 5 10.30-11.30 Wednesday 2 September 2026 | All confirmed participants. |
| Topic: Nature, Environment, Climate Change, Designated Landscapes | Nature recovery, valued landscapes, protecting open spaces, locations for development, coastal change and flooding | Month 6 10.30-11.30 Wednesday 7 October 2026 | All confirmed participants. |
| Drafting, Consulting on and Submitting Your Statement | The importance of a strong vision, best practice, examples. How objectives can set a path to deliver the vision. Using the template, policy maps. Publicising your draft statement and consulting your community. Updating the draft statement. Meeting the conditions, supporting documents, timescales, maps. How NPS will feed into the LP process. | Month 7 10.00-11.00 Wednesday 4 November 2026 | All confirmed participants. |
| Once statement has been drafted, parishes will need to consult on the draft statement for 6 weeks; this is the earliest date that we would expect parishes to be able to do that. |  |  |  |
| Submission | Earliest likely date for submission of NPS after 6 week consultation on draft statement. | Month 8 January 2027 |  |